## Project Info & Doc Control
PROJECT PLAN FOR PROJECTS FUNDED THROUGH DEECA ENVIRONMENT PROGRAMS
PROJECT INFORMATION
Fill in your project details below:
Program Name:
Project ID:
Project Title:
Lead Agency:
Contact Name:
TABLE OF CONTENTS
Project Plan
Tab 1 | Project Info & Document Control | For version control and approval history of the completed project plan. When changes are made to the content of the project plan, the Document Control table should be updated with a summary of the changes and a signature.
Tab 2 | Project Summary | Documents the project objectives, biodiversity assets, stakeholders, governance arrangements, etc.
Tab 3 | Map | Image(s) of project location.
Tab 4 | Activity Plan | Documents the activities, deliverables and budget per financial year. This information will be used to track progress and acquit delivery and expenditure in annual reports.
Tab 5 | Budget | Documents the annual project funding amounts, expense categories and amounts, a breakdown of salaries to be funded, expected co-contributions.
Tab 6 | Risk Assessment | Risk register.
Reporting spreadsheets
Tab 7 | Reporting 2025-26 | For annual reporting on project deliverables and budget expenditure. This tab is to be completed and a copy of this spreadsheet attached to the online 2025-26 Annual Report.
Tab 8 | Reporting 2026-27 | For annual reporting on project deliverables and budget expenditure. This tab is to be completed and a copy of this spreadsheet attached to the online 2026-27 Annual Report.
Useful resources
Tab 9 | Glossary | Gloassary of definitions used in this spreadsheet.
Tab 10 | Variations table | Examples of different types of project variations (e.g. to budget, deliverables, timing).
Tab 11 | Template version history | Document any updates to the template since first distribution.
DOCUMENT CONTROL
Document History |  |  | Approvals
Date dd/mm/yyyy | Author | Summary of changes (e.g. updated project plan with variation to weed control deliverables) | Approver name | Approver title | Signature (insert picture, or refer to an email approval, e.g. email from [name] to [name], [date]) | Date dd/mm/yyyy

## Prjct Summary
PROJECT SUMMARY
0 | Project Title: | 0 | Lead Agency: | 0
Project Location Describe the location of the project in the text box below | DEECA region(s) Select from drop-down list | Parks Victoria region(s) Select from drop-down list (if applicable) | Local government area(s) Select drop-down list below | Catchment Management Authority(s) Select drop-down list below
1. Project activities Briefly (i.e. in 1-2 sentences) describe what will be done in this project (full details to be entered in the Activity Plan tab.) E.g. This project will conduct fox control using baiting and ground shooting in areas
2. Project objectives What are the desired outcomes / effects of the project, including biodiversity and conservation outcomes, by the end of the project? E.g. This project aims to reduce the impact of foxes on threatened species, including local populations of Potoroos.
3. Project rationale Why is this project important? What is happening that means it is needed now? If the project didn't go ahead, what would be the impact? E.g. Potoroos are an endangered species, and without this project, there is a threat of local extinction in X area due to fox predation.
4. Key biodiversity assets List the key species / communities that will directly benefit from this work. Note: this does not have to be exhaustive. The information may be used in public communications or to support information requests. | FFG/EPBC listed species/communities: (maximum 10)
Other key species (e.g. culturally important species): (maximum 10)
5. Public Communications Summary Provide a brief summary of the project in language suitable for the general public. E.g., outline the issue(s) being addressed by the project, location, intended outcomes etc. This informaiton may be used in public communications material such as websites or social media. (maximum 150 words)
6. Animal welfare / ethics considerations
7. Approvals / authorisation requirements | Approvals |  |  | Timeframe dd/mm/yyyy - dd/mm/yyyy
List the relevant permits approvals / authorisations required to allow works to proceed.
8. Exit strategy Describe what will occur if there is no more funding available beyond the end of the project, i.e. describe the transition strategy for the project.
9. Project Stakeholders | Stakeholder |  | Role
List any stakeholders that will be informed, engaged or involved in project delivery.
10. Governance Describe the structures in place to ensure good governance and strategic cooperation between stakeholders across the project’s landscape and different land tenures. E.g. list any Project Control Boards, working groups or steering committees, their decision-making remit and frequency of meeting.
11. Traditional Owner involvement and self-determination Project budgets should include funding to support Traditional Owner decision making and participation in project planning and delivery. Budget allocations are to be listed in the Budget tab. Interested Traditional Owners and Aboriginal community groups must be supportive of the project and have opportunities to be involved in planning and/or delivery of activities. The extent and nature of involvement must be directed by Traditional Owner interests and aspirations. Focus may be placed on building and supporting partnerships with Traditional Owners and Aboriginal Victorians for a coordinated, cross-tenure approach to weed and pest management. For example, opportunities could be identified: · For Aboriginal environmental businesses / employment that support participation in environment management to achieve project deliverables · For capacity building with Traditional Owners on country for protection of Cultural Values · For Traditional Owners to build programs that can assist with working on country · To encourage inclusion of cultural knowledge and values into planning and delivery · To facilitate the project being led by Traditional Owners over time where they have indicated an interest to do so.
List all Traditional Owner groups and RAPs within the project area.
Describe any project linkages with Healthy Country Plans
Describe any requirements relating to Recognition and Settlement Agreements (including Joint Management)
Describe how the project will enable self-determination for Traditional Owners and Aboriginal Victorians.
12. Environmental volunteering opportunities Describe environmental volunteering opportunities that may arise from this project (if any). Note: estimates of volunteer hours are to be added in the Activity Plan tab
13. Complementary / related projects Describe how this project complements any existing projects / programs. Describe how you will interact with those projects / programs to avoid duplication and maximise outcomes. E.g., if there are herbivore, predator or weed control projects underway in the same areas, in what way can this combination enhance biodiversity outcomes?

## Map
MAPS
Insert at least one picture showing your project location on this tab. Picture files should not total more than 8MB. Take a snip from Google maps (i.e. low res jpg)
Map description: | Type description here
Map description: | Type description here
Map description: | Type description here

## ACTIVITY PLAN
ACTIVITY PLAN
INSTRUCTIONS: - Use the table below to record the activities that are planned for your project. - It is important that only deliverables / outputs are recorded here (i.e. on-ground weed/animal control or others such as engagement activities). Please do not separate out expenses or ‘overheads’ that are part of delivering these activities, such as salaries, vehicle costs and project coordination. We want to understand the total cost of delivering each output inclusive of all expenses/overheads. If it is difficult to know how to split expenses such as project coordination between activities, then please simply apportion roughly OR split equally across activities. - Hectare deliverables should be based on the Footprint of Activities to be delivered, see Glossary tab for more info. The Footprint can include areas that have been searched and invasive species controlled where found (regardless of how many animals/weeds were found). - If the hectares of pest control needed is unknown, for example if it won't be determined until after an assessment, please include an estimate of hectares and make a note of this in the comments column.
ACTIVITIES | [7 empty] | DELIVERABLES |  |  | BUDGET | CO-CONTRIBUTIONS
Financial year | Action Refer to table to the right of this tab for full list of Activities associated with each Action. | Activity Select the specific activity to be undertaken. The drop-down list is conditional on the response chosen in the previous column. Refer to table to the right of this tab for full list of Activities associated with each Action. | If "other" was selected in the previous column, specify here Cell will become white if previous column has "other" activity selected | Method Animal control: use separate lines for different methods of control Weed control: either use separate lines for different methods OR select "other" and provide details in the "Purpose" column If the method is to be used is not listed, or is unknown, select “Other”. | Baits/chemicals List any to be used, if applicable E.g. PAPP, 1080 | Site/location OPTIONAL | Purpose OPTIONAL Briefly describe the purpose of the activity | Deliverables | Units of measure Must be hectares for all animal control, weed control and assessment activities. | Other units If "other" was selected in the units column, specify here. Cell will colour white. | Program funding ($) | Cash ($) | Source of cash E.g. State govt. (other than this program), Australian government, local government, private e.g. philanthropic, lead agency of this project | In-kind ($) Note: the value of any volunteer hours should be costed at $44.16 per hour | Source of in-kind E.g. State govt. (other than this program), Australian government, local government, private e.g. philanthropic, lead agency of this project | What will the co-contribution be used for? E.g. volunteer hours: 10hrs x 10 volunteers, equipment, loan of building, or cash for project support | Budget ($) TOTAL | COMMENTS Please make a note here if deliverables are an estimate due to, for example: an assessment needs to take place first. | VARIATIONS If a variation applies, update the relevant activity/targets/budget, and include a comment below describing the amendment. If the variation is a carry forward of budget from the previous year, select the appropriate field in the Financial Year column. E.g. “Variation to budget (reduced from $10,000), Aug 25
Select from drop down | Select from drop down | Select from drop down | Free text | Select from drop down | Free text | Free text | Free text | Enter a number | Select from drop down | Free text | Enter a number | Enter a number | Free text | Enter a number | Free text | Free text | Automatically calculated | Free text | Free text
[17 empty] | 0 |  |  | Table of Actions and Activities (for columns B and C)
[17 empty] | 0 |  |  | assessment | engagement_activity | artificial_habitat | monitoring_structures | pest_herbivore_control | pest_predator_control | revegetation | research_and_monitoring | threatened_species_response | weed__control | other
[17 empty] | 0 |  |  | Assessment_Flora | Conference | Artificial tree hollow | Artificial_substrate | Deer control | Cat control | Revegetation | Research & monitoring - Behaviour | Threatened_species_action | Weed_control | other_specify
[17 empty] | 0 |  |  | Assessment_Fauna | Field day | Artificial or temporary pond | Bore | Fencing | Fencing |  | Research & monitoring - Life history/physiology
[17 empty] | 0 |  |  | Assessment_Habitat_condition | Meeting | Habitat box | Buoy_mooring | Goat control | Fox control |  | Research & monitoring - Threats
[17 empty] | 0 |  |  | Assessment_Management_agreement | Presentation | Man made ground feature | Camera_trap | Horse control | other_specify |  | Research & monitoring - Population and distribution
[17 empty] | 0 |  |  | Assessment_Research_monitoring | Survey | Natural ground feature | Depth_gauge | Pig control |  |  | Other - provide details in Methods tab
[17 empty] | 0 |  |  | Assessment_Revegetation | Training | Other - provide details in Methods tab | Flow_meter | Rabbit control
[17 empty] | 0 |  |  | Assessment_Threatened_species_response | Volunteering event |  | Hide | other_specify
[17 empty] | 0 |  |  | Assessment_Water | Workshop |  | Measuring_station
[17 empty] | 0 |  |  | other_specify | Other - provide details in Methods tab |  | Photo_point
[17 empty] | 0 | [5 empty] | Recruitment_plates
[17 empty] | 0 | [5 empty] | Song_meter
[17 empty] | 0 | [5 empty] | Trap_cage_box_net
[17 empty] | 0 | [5 empty] | Quadrats
[17 empty] | 0 | [5 empty] | Other - provide details in Methods tab
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[7 empty] | Subtotal (hectares): | 0 |  |  | 0 | 0 |  | 0 |  |  | 0

## Budget
BUDGET
Table A - Funding Summary (pre-fills from Activity Plan)
Funding source | 2025-26 | 2026-27 |  | TOTALS
Program Funding (from DEECA) | 0 | 0 |  | 0
Co-contributions - Cash | 0 | 0 |  | 0
Co-contributions - In-kind | 0 | 0 |  | 0
Totals | 0 | 0 |  | 0
Fill out the budget tables below:
Table B - Breakdown of expenses 1. Provide a break down of all expenses associated with the Project (program funding and co-contributions). Refer to the Funding Instructions for definitions of eligible activities and items. 2. The total of the Project Funding column (cell E35) must match the total Project Funding in Table A (E8).
Expense category (select from drop down) | Description of expense Please describe any costs associated with activity including staff costs, equipment, other resources to deliver activity. | Organisation category (select from drop down) | Organisation name (if known) | Project funding $
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | 0 | The total of the Project Funding column (cell E35) must match the total Project Funding in Table A (E8).
0
0
0
TOTAL PROJECT EXPENSES: |  |  |  | 0
*e.g., funding for TOs to participate in meetings. Note: TO involvement in on-ground delivery and cultural heritage assessments should be captured under 'On-ground delivery'.
Table C - Salaries Provide further detail about any salaries that will be paid for using the program funding (e.g. as part of any project management / coordination or on-ground expenses listed in Table B above).
Name of organisation | Position title | Grade level (if applicable) | FTE | Salaries $
0
0
0
0
0
0
0
0
0
0
TOTAL SALARIES: |  |  |  | 0

## 4a. Methods - weeds (hidden)
METHODS - WEED CONTROL and ASSESSMENTS
If your project is delivering weed control or weed assessments, copy and paste line items from tab 3. Activity Plan (columns D to H) and complete details about methods in the table(s) below.
Weed Control and assessment
Activity | Activity details | Site/location | Financial year | Method | Fill in these columns for any planned Weed Assessment |  | Fill in these columns for any planned Weed Control |  |  |  |  | Comments / additional information about delivery methods
[5 empty] | Assessment purpose | What will the Assessment inform? (e.g. treatment plan for financial year XXXX, efficacy of previous year's treatment) | Weed control aim | Target weed species to be controlled (if known) | List any secondary weed species to be controlled (if applicable) | When will the Activity occur? List months or seasons | Describe the treatment plan (if known) E.g. number of treatments, whether treatment is primary or follow-up, whether treatment will cover the entire site or is search & control
COPY/PASTE from tab 3. ACTIVITY PLAN |  |  |  |  | Select from drop down box | Free text | Select from drop down box | Botanical AND common name | List botanical AND common names | Free text | Free text | Optional
Weed control |  | National Park SE | 2026-27 | Manual (e.g. hand pulling; ringbarking) |  |  | Eradication | fdfg | sdgdg | spring- summer
Assessment - weed |  | National Park SE | 2025-26 | Field survey (foot/vehicle) | Search and detect | yr 2 treatment
Note on A3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are we missing any questions/drop-downs in this tab?
Note on H6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change to free text?

## 4b. - Methods - animals (hidden)
METHODS - ANIMAL CONTROL and ASSESSMENTS
If your project is delivering animal control or assessments, copy and paste line items from tab 3. Activity Plan (columns D to H) and complete details about methods in the table(s) below.
Animal control and assessment
Activity | Activity details | Site/location | Financial year | Method | Describe the methods planned | Fill in these columns for any planned Assessment | Fill in these columns for any Monitoring structures used |  |  | Fill in these columns for any planned Baiting | [6 empty] | Fill in these columns for any planned Trapping |  | Fill in these columns for any planned Aerial Shooting | Fill in these columns for any planned Ground Shooting | Fill in these columns for any planned Fencing | [5 empty] | Fill in this column for any planned Rabbit Control | Comments / additional information about delivery
[6 empty] | What is the purpose of the Assessment? (e.g. to inform treatment plan for financial year XXXX, to determine efficacy of previous year's treatment) | Type | Purpose | Details (number of structures, location, when they will be checked etc) | Bait type | Estimated number of bait stations (or specify if bait trail) | Estimated density of bait stations (If applicable) | Estimated frequency of check & replace | Estimated baiting period | Estimated duration of pulse | Estimated break between pulses | Estimated no. of trap sites | Estimated duration of trapping over the life of the project | Estimated number of shooter hours over the life of the project (number of shooters multiplied by number of hours) | Estimated number of shooter hours over the life of the project (number of shooters multiplied by number of hours) | Stage of delivery | Purpose | Change in access | Species access change | Fence type | Length of fencing installed / repaired | When will the Activity occur? List months or seasons for each treatment method
COPY/PASTE from tab 3. ACTIVITY PLAN |  |  |  |  | Free text | Free text |  | Free text | Free text | Free text | Enter a whole number OR type 'bait trail' | No. bait stations per km2 | Select from drop down box | No of pulses per year | Number of weeks | Number of weeks | Enter a whole number | Number of weeks | Enter a whole number | Enter a whole number | Select from drop down box | Select from drop down box | Select from drop down box | Select from drop down box | Select from drop down box | Metres | Free text | Optional
Fox control | NA | National Park NW | 2526 | Bait
Cat control | NA | National Park NW | 2627 | Trap
Pig control | NA | National Park SE | 2526 | Trap
[1] If you plan to conduct animal contol of a species not listed in the drop down box in this worksheet, include it in the worksheet titled "5. Other Activities". [2] For example: aerial shooting, baiting, biological control (specify), destroy in situ, disturb, fertility control, fencing, fumigation, ground shooting, harbour destruction, manual removal, mustering, translocation, trapping [3] Only fill in the columns relevant for the treatment methods being used for that Activity. For example, if conducting baiting and trapping to control foxes, only fill in the columns for baiting and trapping.
Note on A3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are we missing any questions/drop-downs in this tab?

## 4c.Methods-all other activities (hidden)
DETAILS - ALL OTHER ACTIVITY
If your project is delivering animal control or assessments, copy and paste line items from tab 3. Activity Plan (columns D to H) and complete details in the table(s) below.
Other activities
Activity | Activity details | Site/location | Financial year | Method | Describe the methods planned | Describe the purpose | Fill in these columns for any planned Research & monitoring |  |  | Fill in these columns for any planned Threatened species response |  |  | Comments / additional information about delivery
[7 empty] | Type | Species | Specific activity | Purpose category | Type | Number of individuals
COPY/PASTE from tab 3. ACTIVITY PLAN |  |  |  |  | Free text | Free text | Select from drop down box | Free text | Select from drop down box | Select from drop down box | Select from drop down box | Entre a whole number | Optional
Other activity | Engagement event | National Park SE | 2627 | NA | Community weed ID workshop held in community centre | Support local landholders to control weeds on their properties |  |  |  | Restore biological community | Establish new population
[10 empty] | Restore individual species | Captive breeding
Note on A3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are we missing any questions/drop-downs in this tab?

## Reporting (hidden)
REPORTING
Project ID: | 0 | Project name: | 0 |  | Lead agency: | 0
Fill in this spreadsheet to report on the Activities delivered during the reporting period. If a cell doesn't apply, write "NA". Note: this spreadsheet compliments the reporting form to be completed on GrantsOnline.
TARGETS This section is pre-filled from tab.3 Activity Plan | [7 empty] | What was delivered?
[8 empty] | Deliverables achieved |  | Budget spent |  |  | Variations |  | Co-contributions |  |  | Methods used |  | Results/outcomes
Activity | Activity details | Site/location | Financial year | Method | Deliverable | Units | Budget | Did you meet (or exceed) your Targets for this reporting period? For on-ground Activities refer to your spatial mapping for the quantity of hectares delivered (Select from drop down box) | If no, provide a brief description of the reason why | How much budget was spent on this Activity? ($) | Variance - budget expended Calculated automatically | If there is a variance in the budget spent, provide a brief description of the reason why | Have you requested a Variation for any variance(s) in Targets or budget? Select from drop down box | If you have an underspend or under-delivery of targets, how you are going to manage this going forward? I.e. how are you going to make up the remaining targets, and/or make sure budget is spent? | Co-contribution: Cash ($) | Co-contribution: In-kind ($) | Total amount spent ($) Calculated automatically | Was the Activity delivered as described in the Details section of your Project Plan? (Select from drop down box) | If anything was done differently, provide a brief description of what and why. E.g. | Describe any results or outcomes of the Activity E.g. Who and how many were engaged for an engagement activity
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Yes (met or exceeded) |  | 50000 | #REF! |  | No | NA | 10000 |  | 60000 | Yes - Activity delivered as planned | NA | dfghdfhhsf
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! |  |  |  | 10000 |  | 10000
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! |  |  |  | 0 |  | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | [5 empty] | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | [5 empty] | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | [5 empty] | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! |  |  |  |  | 2000 | 2000
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | [5 empty] | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | [5 empty] | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | [5 empty] | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | [5 empty] | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | [5 empty] | 0
TOTALS |  |  |  |  | #REF! |  | #REF! | 0 |  | 50000 | #REF! |  |  |  | 20000 | 2000 | 72000
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do we include reporting in this spreadsheet? Pros: - Project leads have the project plan targets and $ right in front of them and pre-filled, so there is less room for error (e.g. reporting against the wrong targets, or from old variation). - EP team can copy/paste reporting info direct into a master s/s. If we structure the s/s well, it only requires one copy/paste per project. Cons: - this spreadsheet becomes bigger and more complex... Reply: @Diana C Shrimpton (DEECA) good questions D, sounds goof having pre-filled approved target metrics. Also are we going to have a page 2 or have it all here on one page for reporting for a checklist and details of > as per project deliverables required as outlined in the Word Project Plan ?
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Diana C Shrimpton (DEECA) As discussed Diana, no UOM and quantities reported on here as advised this will be found by ECP GIS spatial analysis, one exception is staffing cost as FTE for the whole reporting period or number of staff and number of staff hours or days ? I guess this will be targeted in the columns (here E to G) but reporting what was actually achieved ? Reply: @Diana C Shrimpton (DEECA) Diana - Also should add a column for who/what org. delivered and how much ? E.g. TO’s, contractor, volunteer, agency staff, for such as 500 person hours, or number of TO’s and UOM days, hours or FTE’s ? Captured in GEMS by the looks...will look at format when you send through.
Note on P5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: Is it important to know where the contributions came from? Reply: @Diana C - For NF we need to break down non govt private and philanthropic contributions as well as other government contributions. Reply: @Sylvia Majetic (DEECA) could please you share a NF report so I can model this section on it? Thanks!

## Risk
RISK ASSESSMENT
This risk assessment matrix is a high level documentation of how you will manage key project risks: - Health and safety risks (including use of chemicals and firearms) - Financial risks - Environmental risks (including non-target risks associated with management) - Organisational/reputational risk (including any political/social risks associated with invasive species control) - Project delivery risk (including impact to targets or timeframes due to resourcing, approvals, site access etc.) Please reference your local level operational risk management tools and documentation that should be available upon request.
|  |  |  | CURRENT (INITIAL) ASSESSMENT |  |  |  | REVISED ASSESSMENT AFTER TREATMENT |  |  |  | Comments
Risk ID | Risk | Cause | Consequence | Likelihood | Consequence | Current Score | Treatment Actions - for significant or high risks | Likelihood | Consequence | Residual Score | Risk Owner | Notes
Nominal id | Immediate effects of the risk occurring | Circumstances which give rise to the risk | Consequences if the risk is realised | Select a value which represents the likelihood that the risk will occur (1=rare, 2=unlikely, 3=possible, 4=likely 5=almost certain) | Select a value which represents the consequence of the risk will occur (1=negligible, 2=minor, 3=moderate, 4=major, 5=extreme) | Select from table (see right) |  | Select a value which represents the likelihood that the risk will occur (1=rare, 2=unlikely, 3=possible, 4=likely 5=almost certain) | Select a value which represents the consequence of the risk will occur (1=negligible, 2=minor, 3=moderate, 4=major, 5=extreme) | Select from table (see right) | Person most suited to managing the risk
1 | (Example only - delete if not applicable) Difficulty in sourcing contractors and staff / contractors and staff movements restricted | COVID 19 | Delays to project activities | Possible | Moderate | Medium | Undertake planning, procurement and other office-based activities during movement restrictions. | Rare | Minor | Low | [insert name here]
Mobilise once restrictions lifted.
Continue to deliver activities as per COVID roadmaps and guidelines.
2 |  |  |  | Rare | Extreme | Significant |  |  |  | #N/A
3 | [5 empty] | #N/A |  |  |  | #N/A
4 | [5 empty] | #N/A |  |  |  | #N/A
5 | [5 empty] | #N/A |  |  |  | #N/A
6 | [5 empty] | #N/A |  |  |  | #N/A
7 | [5 empty] | #N/A |  |  |  | #N/A
8 | [5 empty] | #N/A |  |  |  | #N/A
9 | [5 empty] | #N/A |  |  |  | #N/A
10 | [5 empty] | #N/A |  |  |  | #N/A
11 | [5 empty] | #N/A |  |  |  | #N/A
12 | [5 empty] | #N/A |  |  |  | #N/A
13 | [5 empty] | #N/A |  |  |  | #N/A
14 | [5 empty] | #N/A |  |  |  | #N/A
15 | [5 empty] | #N/A |  |  |  | #N/A
CONSEQUENCE
LIKELIHOOD

## Reporting 25-26
REPORTING |  |  | 2025-26 |  |  | Program admin. only: |  | Draft
Use this tab to report on the targets achieved and budget spent over the last financial year. Your deliverables for this financial year are pre-filled below. Scroll to the table on the right hand side to answer questions about your delivery. Refer to the reporting information webpage for further information:
Environments Program Reporting webpage LINK
DELIVERABLES (FROM ACTIVITY PLAN) | [19 empty] | REPORTING
ACTIVITIES | [7 empty] | DELIVERABLES |  |  | PROGRAM BUDGET | CO-CONTRIBUTIONS |  |  |  |  | BUDGET TOTAL ($) | COMMENTS | VARIATIONS | Deliverables achieved |  | Budget spent |  |  | Next steps | Co-contributions | [6 empty] | TOTAL | Methods | Comments | Pest animal control metrics
Financial year | Action | Activity | Other Activity details | Method | Baits / chemicals | Site/Location | Purpose | Deliverables | Units of measure | Other units | Program funding ($) | Cash ($) | Source of cash | In-kind ($) | Source of in-kind | What will the co-contribution be used for? |  |  |  | Did you meet your Deliverables for this reporting period? For on-ground Activities refer to your spatial mapping for the quantity of hectares delivered | If no, briefly describe why | Budget expenditure How much program funding was spent on this Activity? ($) | Variance - budget expended | Explanation - expenditure variance If there is a variance in the budget spent, briefly describe why | If you haven't met your deliverables and/or budget expenditure targets, how will you manage this? I.e. how will you make up the remaining deliverables or spend the remaining budget? | Cash ($) | Source of cash | Variance - Cash co-contribution | In-kind ($) For volunteer hours use a value of $44.16/hr | Source of in-kind | Variance - In-kind con-contribution | Explanation - variances If any | Total spent: program funding + co-contributions ($) | Did you change your methods from the Activity Plan? If so, provide a brief description of what and why. | E.g. about results or outcomes OPTIONAL
Automatically copied from Activity Plan | [19 empty] | Select from drop down | Free text | Enter a number | Calculated automatically | Free text | Free text | Enter a number | Select from drop-down | Calculated automatically | Enter a number | Select from drop-down | Calculated automatically |  | Calculated automatically | Free text | Free text |  | Number of pest animals controlled (by method) |  |  |  |  | Comments
#NAME? | [22 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  |  | Ground shoot | Aerial shoot | Trapping | Baiting | Other | OPTIONAL
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  |  | Number | Number | Number | Percentage bait take | Free text | Free text
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Deer - Sambar
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Deer - Fallow
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Deer - Red
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Deer - Hog
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Rabbit
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Pig
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Goat
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Horse
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Fox
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Cat
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Other (specify)
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Ground / aerial shooting metrics
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  |  | Ground shoot | Aerial shoot | Comments (optional) OPTIONAL
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  |  | Number | Number | Free text
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Shooter nights/days
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Shooter hours
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[7 empty] | Subtotal (hectares): | 0 | Hectares |  | 0 | 0 |  | 0 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  | 0

## Reporting 26-27
REPORTING |  |  | 2026-27 |  |  |  | Program admin. only: | Draft
Use this tab to report on the targets achieved and budget spent over the last financial year. Your deliverables for this financial year are pre-filled below. Scroll to the table on the right hand side to answer questions about your delivery. Refer to the reporting information webpage for further information:
Environments Program Reporting webpage LINK
DELIVERABLES (FROM ACTIVITY PLAN) | [19 empty] | REPORTING
ACTIVITIES | [7 empty] | DELIVERABLES |  |  | PROGRAM BUDGET | CO-CONTRIBUTIONS |  |  |  |  | BUDGET TOTAL ($) | COMMENTS | VARIATIONS | Deliverables achieved |  | Budget spent |  |  | Next steps | Co-contributions | [6 empty] | TOTAL | Methods | Comments | Pest animal control metrics
Financial year | Action | Activity | Other Activity details | Method | Baits / chemicals | Site/Location | Purpose | Deliverables | Units of measure | Other units | Program funding ($) | Cash ($) | Source of cash | In-kind ($) | Source of in-kind | What will the co-contribution be used for? |  |  |  | Did you meet your Deliverables for this reporting period? For on-ground Activities refer to your spatial mapping for the quantity of hectares delivered | If no, briefly describe why | Budget expenditure How much program funding was spent on this Activity? ($) | Variance - budget expended | Explanation - expenditure variance If there is a variance in the budget spent, briefly describe why | If you haven't met your deliverables and/or budget expenditure targets, how will you manage this? I.e. how will you make up the remaining deliverables or spend the remaining budget? | Cash ($) | Source of cash | Variance - Cash co-contribution | In-kind ($) For volunteer hours use a value of $44.16/hr | Source of in-kind | Variance - In-kind con-contribution | Explanation - variances If any | Total spent: program funding + co-contributions ($) | Did you change your methods from the Activity Plan? If so, provide a brief description of what and why. | E.g. about results or outcomes OPTIONAL
Automatically copied from Activity Plan | [19 empty] | Select from drop down | Free text | Enter a number | Calculated automatically | Free text | Free text | Enter a number | Select from drop-down | Calculated automatically | Enter a number | Select from drop-down | Calculated automatically |  | Calculated automatically | Free text | Free text |  | Number of pest animals controlled (by method) |  |  |  |  | Comments
#NAME? | [22 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  |  | Ground shoot | Aerial shoot | Trapping | Baiting | Other | OPTIONAL
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  |  | Number | Number | Number | Percentage bait take | Free text | Free text
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Deer - Sambar
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Deer - Fallow
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Deer - Red
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Deer - Hog
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Rabbit
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Pig
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Goat
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Horse
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Fox
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Cat
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Other (specify)
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Ground / aerial shooting metrics
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  |  | Ground shoot | Aerial shoot | Comments (optional) OPTIONAL
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  |  | Number | Number | Free text
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Shooter nights/days
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | Shooter hours
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[23 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  | 0
[7 empty] | Subtotal (hectares): | 0 | Hectares |  | 0 | 0 |  | 0 |  |  | 0 |  |  |  |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  | 0

## Glossary
GLOSSARY
Term | Definition
Activity | The process of using labour and materials to achieve outcomes for biodiversity, e.g. weed control, animal control, assessments, management plans to support long term weed or animal control, engagement events to inform or educate the general public
Activity Area | The area over which a particular Activity takes place, measured in hectares. E.g., 1,000ha weed assessment; 500ha of weed control.
(see diagram below) | The Activity Area is found by combining all the buffered Treatment Areas for a particular Activity. Buffering of Treatment Areas must be in accordance with DEECA Activity Reporting guidelines for weed and pest animals.
Activities that are conducted on-ground (i.e., weed control, pest animal control, assessments, monitoring activities), have an associated Activity Area.
Other Activities (such as management plans and engagement events) won’t have an associated Activity Area. Alternative units should be assigned in your Activity Plan as appropriate. E.g., 2 community engagement events, 1 management plan.
The Activity Area for weed and animal control Activities should include the entire area where weeds/animals are searched for and treated where present (regardless of how many are found).
When a weed or animal search is undertaken separately to control Activities (i.e., at a different time), this should be recorded as an assessment rather than weed or animal control.
Where multiple Activity Areas of the same type overlap (e.g., where the same 100ha is sprayed for weeds three times over the course of a financial year; or if the buffered points where deer are controlled overlap), the spatial data for each Activity Area are dissolved to find the Footprint in hectares.
Acquittal of on-ground Activities is done based on the Footprint.
Activity Plan | The Plan for delivery of biodiversity management actions in agreed timeframes and locations with hectare targets for each financial year. The Activity Plan forms part of the Project Plan.
Approved Location | Areas approved (via the spatial data submitted as part of this Project Plan) within which specific Activities may be undertaken. E.g., Fox control activities may be undertaken anywhere within the Approved Location for Fox Control.
(see diagram below)
Assessment | A site-specific evaluation of the condition, outcomes or management issues present/absent in a landscape to assist decision making about management (threat control) activities. Assessment may be undertaken pre and/or post treatment (e.g., to enable adaptation of control approaches) and may be desktop or field based. Assessments may not necessarily lead to management actions, e.g., if threats are not found to be present.
Weed Assessments or Animal Assessments should be included as Activities with associated Deliverables in the Project Plan and be reported on spatially each financial year.
Deliverable (see diagram below) | The measurable outputs contracted to be achieved by a project within a financial year as agreed in the Activity Plan. E.g., 100ha of weed assessment; 25ha of weed control; 1,000ha of fox control (baiting); 15,00ha of fox control (trapping); 2 engagement events.
Delivery Agent | The organisations delivering services / activities. Could be either the Lead Agent or a Delivery Partner operating under the direction of the Lead Agent.
Footprint | The maximum extent of the area (measured in hectares) under management, found by dissolving the spatial data for Activity Areas of the same type within a financial year.
(see diagram below) | Acquittal of on-ground Activities is done based on the Footprint (ha) reported spatially for each financial year.
The Footprint is also used to calculate the contribution of Activities to the relevant Bio2037 targets.
Lead Agent | The organisation administering delivery of services in accordance with the Project Plan, with funding received via a funding agreement with DEECA.
Monitoring | A regular, systematic process to monitor the effectiveness or outcomes of biodiversity management Activities on a target species, community, or landscape
Project Area | The total area of all Approved Locations managed as one project by a Lead Agent.
(see diagram below) | The boundary of the Project Area should follow the boundary of the Approved Locations. If Approved Locations are separated geographically, the Project Area will cover multiple locations (i.e., should be recorded as multiple polygons in your spatial data).
Treatment Area | The location(s) where an Activity is delivered. E.g., the location where a deer is shot; the track log for weed control.
The combination of all buffered Treatment Areas for a particular Activity gives the Activity Area (measured in hectares).
Treatment Method | The method used to achieve an Activity. E.g., baiting, trapping, harbour destruction.

## Hidden - Risk Lookup (hidden)
Risk Matrix | Consequence
Likelihood |  | BENEFIT (+) |  |  |  |  | HARM (-)
|  | 5 | 4 | 3 | 2 | 1 | -1 | -2 | -3 | -4 | -5
|  | Extreme | Major | Mod | Minor | Neg | Neg | Minor | Mod | Major | Extreme
| 5 | High | High | High | Significant | Medium | Medium | Significant | High | High | High
| 4 | High | High | Significant | Medium | Medium | Medium | Medium | Significant | High | High
| 3 | High | Significant | Medium | Medium | Low | Low | Medium | Medium | Significant | High
| 2 | Significant | Medium | Medium | Low | Low | Low | Low | Medium | Medium | Significant
| 1 | Significant | Medium | Low | Low | Low | Low | Low | Low | Medium | Significant
|  | Risk Matrix | Consequence
| Likelihood |  | HARM (-)
|  |  | 1 | 2 | 3 | 4 | 5
|  |  | Negligible | Minor | Moderate | Major | Extreme
|  | Almost certain | Medium | Significant | High | High | High
|  | Likely | Medium | Medium | Significant | High | High
|  | Possible | Low | Medium | Medium | Significant | High
|  | Unlikely | Low | Low | Medium | Medium | Significant
|  | Rare | Low | Low | Low | Medium | Significant
| Score | Likelihood Rating
| 1 | Rare
| 2 | Unlikely
| 3 | Possible
| 4 | Likely
| 5 | Almost certain
| Score | Consequence
| 1 | Negligible Harm
| 2 | Minor Harm
| 3 | Moderate Harm
| 4 | Major Harm
| 5 | Extreme Harm

## Variations table
VARIATIONS
Changes to the following controls (timing, scope, budget, risks) will require a written notification to the Program Team and may require a variation to the funding agreement.
The following table identifies the circumstances in which the Project Lead organisation needs to either inform or make a request to the Program Team and the timing for these notifications.
Control | Change / situation | Example | Type and timing of notification required
Timing | Moving Activities from one financial year to another. | E.g., conduct weed control in 2023-24 instead of in 2022-23 due to unfavourable environmental conditions. | Request ASAP before proceeding (variation may be required)
| Anticipated reporting delays. | E.g., if it is anticipated that a progress report is unlikely to be completed by the due date. | Request in advance of due date
| Anything that affects project completion date | E.g. it is anticipated that project activities are unable to be completed by the project end date. | Request ASAP (variation may be required)
Scope | Changing the Activities to be undertaken by the project. | E.g., organisation wishes to remove an Activity that is listed in the Activity Plan (such as fox control) and replace it with a different Activity (such as rabbit control) that is not listed in the Activity Plan. | Request before proceeding (variation may be required)
E.g., organisation wishes to conduct a cultural burn instead of an engagement event.
| Changing the location of Activities to outside of the Approved Location for that Activity. | E.g., lead agent wants to conduct fox control outside of the Approved Location for fox control depicted in the shapefile submitted with the Project Proposal. | Request before proceeding (variation may be required)
Note: A further assessment against the latest version of SMP will be required
| Changes to the Deliverables for any Activity. | E.g., organisation wishes to scope down the target for hectares of weed control (e.g., due to new information being available about the extent of the weed infestation). | Request ASAP (variation may be required)
| Changing the Treatment Method used to undertake an Activity or any other details recorded in the Activity Details section of the Activity Plan. | E.g., weed control is completed using a different treatment method to that listed in the Activity Plan | Inform (as part of the next Annual Report)
E.g., the method used for controlling pigs is changed from baiting to trapping
Budget | Move budget between agreed Activities. | E.g., $10,000 is used for rabbit control instead of fox control. Both rabbit and fox control are listed in the Activity Plan. There is no change to the planned hectare Deliverables for either Activity. | Inform as soon as possible (variation may be required)
| Spend excess (unspent) budget to increase on-ground delivery of an Activity within the Approved Location for that Activity. | E.g., a weed control project has met its hectare targets but still has $10,000 left in its budget. Organisation wants to use this funding to treat additional hectares (over and above the planned Deliverables) within the area agreed in the project plan. | Inform (as part of the next report)
| Spend excess (unspent) budget on an item or Activity that does not relate to existing agreed Activities. | E.g. a weed control project has met its hectare Deliverables but still has $10,000 left in its budget. Organisation wants to use this funding for Fox Control on the site. | Request before proceeding (variation may be required)
| Move budget between financial years | E.g. carryover unspent budget into a subsequent financial year due to savings on Activities. | Request (ASAP; variation required)
E.g. reduce subsequent year budget for planned Activities due to over-expenditure in current financial year.
Risks / Issues | Risks to: | E.g. assessments reveal that pest animals or plants are not present on the site / cover a smaller area than expected / or are present in a different location, resulting in inability to deliver the hectare targets in the agreed location. | Inform as soon as possible (variation may be required)
| - delivery of Activities | E.g. contractor unavailability for animal control results in delays to budget expenditure.
| - delivery of Deliverables | E.g. a natural disaster prevents access to the site.
| - expenditure of yearly budget | E.g. a staff member is unwell and reporting is delayed.
- delivery in the Approved Locations
- delivery of reports by due dates
- or any emerging high or significant rated risks, including OHS risks.

## Template version history
TEMPLATE VERSION HISTORY
Version number | Date dd/mm/yyyy | Author | Summary of changes (e.g. formatting fix)
1.1 | 2025-06-01 | Diana Shrimpton | Original version
1.2 | 2025-06-19 | Adam Hughes | Prjct Summary tab - Local government area list updated; Melbourne Water added to CMA list. Map tab - fix to unlock cells to allow insertion of maps.
1.3 | 2025-07-10 | Adam Hughes | Prjct Summary tab - further fix to enable all Local government areas to be displayed in the drop-down list.
1.4 | 2025-07-22 | Adam Hughes | Methods tab deleted - no longer required. Budget tab - Table B, cell E35 - conditional formatting set to match all funding contributions in Table A cell E8 (program funding plus co-contributions). Template version history tab added.
1.5 | 2025-07-23 | Diana Shrimpton Adam Hughes | Activity Plan tab - columns M and O changed to free text. Instructions (row 2) updated. Reference table of Activities and Actions added. Remove references to Methods tab throughout spreadsheet. Budget tab - Project co-ordination removed from drop down list in Table B, column A. Project Info & Doc Control tab - Table of Contents updated
1.6 | 2025-07-28 | Diana Shrimpton Adam Hughes | Activity Plan tab - added "other" to Method column drop-down for animal control activities. Added baits / chemicals column.

## Hidden - activities lookup (hidden)
ACTION |  |  | ACTIVITY | [10 empty] | METHOD
|  | relates to methods: | assessment | engagement_activity | artificial_habitat | monitoring_structures | pest_herbivore_control | pest_predator_control | revegetation | research_and_monitoring | threatened_species_response | weed__control | other
pest_herbivore_control | Pest animal or overabundant exotic or native wildlife management. | animal control | Assessment_Flora | Conference | Artificial tree hollow | Artificial_substrate | Deer control | Cat control | Revegetation | Research & monitoring - Behaviour | Threatened_species_action | Weed_control |  | Animal control - Aerial shoot | Animal control - Aerial shoot
pest_predator_control | Pest animal or overabundant exotic or native wildlife management. | animal control | Assessment_Fauna | Field day | Artificial or temporary pond | Bore | Fencing | Fencing |  | Research & monitoring - Life history/physiology |  |  |  | Animal control - Bait | Animal control - Ground shoot
weed__control | Weeds, overabundant or out of range native plant management | weed control | Assessment_Habitat_condition | Meeting | Habitat box | Buoy_mooring | Goat control | Fox control |  | Research & monitoring - Threats |  |  |  | Animal control - Biological | Animal control - Trap
threatened_species_response | Actions taken to manage threatened species | threatened_species_response assessment monitoring structures | Assessment_Management_agreement | Presentation | Man made ground feature | Camera_trap | Horse control | other_specify |  | Research & monitoring - Population and distribution |  |  |  | Animal control - Destroy in situ | Animal control - Other
assessment | Assessments for information gathering that may or may not lead to management actions. | assessment monitoring structures | Assessment_Research_monitoring | Survey | Natural ground feature | Depth_gauge | Pig control | [6 empty] | Animal control - Disturb | NA - provide details in Purpose column
monitoring_structure | Revegetating or restoring (often cleared) land, and marine and coastal environments. | revegetation | Assessment_Revegetation | Training | Other | Flow_meter | Rabbit control |  |  | Assessment - Flora |  |  |  | Animal control - Fertility control
revegetation_restoration | Research and monitoring to fill knowledge gaps | assessment monitoring structures | Assessment_Threatened_species_response | Volunteering event |  | Hide | other_specify |  |  | Assessment - Fauna |  |  |  | Animal control - Fencing | Animal control - Fencing
research_monitoring |  | na | Assessment_Water | Workshop |  | Measuring_station |  |  |  | Assessment - Habitat condition |  |  |  | Animal control - Fumigate | Animal control - Other
engagement_event |  | na | other_specify | Other |  | Photo_point |  |  |  | Assessment - Management agreement |  |  |  | Animal control - Ground shoot
habitat_feature |  | other |  |  |  | Recruitment_plates |  |  |  | Assessment - Research & monitoring |  |  |  | Animal control - Harbour destruction
other | [5 empty] | Song_meter |  |  |  | Assessment - Revegetation |  |  |  | Animal control - Manual removal
[6 empty] | Trap_cage_box_net |  |  |  | Assessment - Threatened species response |  |  | other_specify | Animal control - Muster
[6 empty] | Quadrats |  |  |  | Assessment - Water |  |  |  | Animal control - Translocate
[6 empty] | Other | [7 empty] | Animal control - Trap
Animal control - Other
Assessment - Desktop / Literature review
[11 empty] | Fencing |  |  | Assessment - Field Survey - Aerial - Drone
[11 empty] | Assessment - Flora |  |  | Assessment - Field Survey - Aerial - Fixed wing
[11 empty] | Assessment - Fauna |  |  | Assessment - Field Survey - Aerial - Helicopter
[11 empty] | Assessment - Habitat condition |  |  | Assessment - Field Survey - Transects - Sign or impacts
[11 empty] | Assessment - Management agreement |  |  | Assessment - Field Survey - Biological sampling
[11 empty] | Assessment - Research & monitoring |  |  | Assessment - Field Survey - Genetic sampling
[11 empty] | Assessment - Revegetation |  |  | Assessment - Indirect survey (e.g. track or scat analysis)
[11 empty] | Assessment - Threatened species response |  |  | Assessment - Model
[11 empty] | Assessment - Water |  |  | Assessment - Vegetation impact survey
[11 empty] | Research & monitoring - Behaviour |  |  | Assessment - Other
[11 empty] | Research & monitoring - Life history/physiology |  |  | Monitoring structure - Artificial substrate
[11 empty] | Research & monitoring - Threats |  |  | Monitoring structure - Bore
[11 empty] | Research & monitoring - Population and distribution |  |  | Monitoring structure - Buoy / mooring
[11 empty] | other_specify |  |  | Monitoring structure - Camera trap
Monitoring structure - Depth gauge
Monitoring structure - Flow meter
Monitoring structure - Hide
Monitoring structure - Measuring station
Monitoring structure - Photo point
Monitoring structure - Recruitment plates
Monitoring structure - Song meter
Monitoring structure - Trap (cage / box / net)
Monitoring structure - Quadrats
Monitoring structure - Other
Other
Revegetation - Aerial sowing
Revegetation - Artificial kelp
Revegetation - Brush mulching
Revegetation - Direct sowing
Revegetation - Hydro mulching
Revegetation - Long-stem planting
Revegetation - Maintenance
Revegetation - Seedbank introduction
Revegetation - Seedling planting
Revegetation - Soil preparation
Other
Weed control - Biological
Weed control - Chemical
Weed control - Manual
Weed control - Mechanical
Weed control - Fire (burning)
Weed control - Heat
Other
Thrt sp response - Caging
Thrt sp response - Captive breeding
Thrt sp response - Collect/ store seed or vegetative material
Thrt sp response - Connectivity interventions
Thrt sp response - Cryobanking
Thrt sp response - Establish new population
Thrt sp response - Fenced-wild captive breeding
Thrt sp response - Genetic interventions
Thrt sp response - Genetic testing
Thrt sp response - Germplasm
Thrt sp response - Inoculate soil
Thrt sp response - Pollination
Thrt sp response - Propagation
Thrt sp response - Species introduction/ reintroduction
Thrt sp response - Supplementary watering/feeding
Thrt sp response - Wild to wild translocation.
Other

## Hidden - Lookup (2) (hidden)
Attributes Lookup |  |  |  | Unprotect sheet: EP
Unprotect worksheets: BOA
Common Attributes | [16 empty] | LOOKUPS for ACTIVITY PLAN
LOOKUPS for REPORTING
Common Attributes are to be supplied for each feature by the person providing the data to DEECA, usually the ‘Delivery Agent’ being the organisation managing the program or project. | [16 empty] | ACTIVITIES |  | METHODS | UNITS OF MEASURE |  | YEAR
Attribute (field) | Reporting standard name and version | Year activity delivered | Fund Source | Project Id | Delivery agent | Delivery agent name | Planned management outcome | Environment |  | Yes | Yes (met or exceeded) |  | Yes - Activity delivered as planned |  | Draft |  | Animal control - Fox | ANIMAL CONTROL METHODS | Animal control - Baiting | hectares |  | 2025-26
shapefile field abbr | stdVersion | yearActDel | fundSource | projectID | DeliverAg | DelivAgNam | MgtOutcome | Environmnt |  | No | No |  | No - Activity delivered with different method |  | Complete and locked |  | Animal control - Deer |  | Animal control - Biological | km |  | 2026-27
Valid value | Bio 2037 V1.0 | Year | Name of State Government funding program |  | Catchment Management Authority |  | Amenity | Estuarine |  |  |  |  | No - Activity not delivered |  |  |  | Animal control - Rabbit |  | Animal control - Fertility control | m |  | 2026-27 (carry forward)
| DELWP Output data standard V2.0 |  | Name of Federal Government funding program |  | Coastcare |  | Accessibility | Marine and Coasts | [8 empty] | Animal control - Pig |  | Animal control - Fencing | other (specify)
|  |  | Local Government |  | Community Group |  | Awareness | River and stream | [8 empty] | Animal control - Goat |  | Animal control - Fumigate
|  |  | Philanthropic |  | DEECA |  | Collaboration | Terrestrial | [8 empty] | Animal control - Cat |  | Animal control - Ground shoot
|  |  | Corporate |  | Friends-of Group |  | Connection to Country | Wetland | [8 empty] | Animal control - Horse |  | Animal control - Harbour destruction
|  |  | Private funding |  | Government Agency |  | Cultural Heritage | [9 empty] | Weed control |  | Animal control - Aerial shoot
|  |  | Nil |  | Landcare |  | Environmental water |  |  | Likelihood | Consequence | Risk rating |  |  |  |  | Assessment - Flora |  | Animal control - Manual removal
[5 empty] | Local Council |  | Extreme event preparedness |  |  | Rare | Negligible | Low |  |  |  |  | Assessment - Fauna - Fox |  | Animal control - Trapping
[5 empty] | Management Committee |  | Farm Water |  |  | Unlikely | Minor | Medium |  |  |  |  | Assessment - Fauna - Deer |  | Animal control - Translocate
[5 empty] | Non-government Org |  | Governance |  |  | Possible | Moderate | Significant |  |  |  |  | Assessment - Fauna - Rabbit
[5 empty] | Not for Profit Org |  | Groundwater |  |  | Likely | Major | High |  |  |  |  | Assessment - Fauna - Pig
[5 empty] | Parks Victoria |  | Habitat available |  |  | Almost certain | Extreme | [5 empty] | Assessment - Fauna - Goat
[5 empty] | Private Land Manager |  | Productivity | [9 empty] | Assessment - Fauna - Cat | WEED CONTROL METHODS
[5 empty] | Research Organisation |  | Skills | [9 empty] | Assessment - Fauna - Horse |  | Weed control - Biological
[5 empty] | Traditional Owner |  | Soil properties |  |  | co-contributions | organisations | [5 empty] | Assessment - Fauna - Other |  | Weed control - Chemical and/or Manual (spray, cut and fill, stem/bark application, drill and fill, cut and paint, hand pulling; ringbarking)
[5 empty] | Trust for Nature |  | Soil stability |  |  | State government (other than this program) | lead agency | [5 empty] | Engagement Event |  | Weed control - Mechanical (e.g. mulching, mechanical pulling; digging/chipping, Mowing; Brush cutting; Cutting/falling;)
[5 empty] | Volunteers |  | Species control |  |  | Australian government | contractor | [5 empty] | Research and Monitoring |  | Weed control - Fire (burning)
[5 empty] | Water Corporation |  | Species recovery |  |  | Local government | traditional owner | [5 empty] | Management Plan |  | Weed control - Heat
[5 empty] | Other |  | Vegetation extent |  |  | Private (e.g. philanthropic) | volunteers | [5 empty] | Traditional Owner involvement
[7 empty] | Vegetation structure and diversity |  |  | Lead agency | other agency | [5 empty] | Other activity
[7 empty] | Water quality |  |  | Volunteers
Weed Control | [17 empty] | ASSESSMENT METHODS | Field survey - Foot
Weeds, overabundant or out of range native plant management. | [16 empty] | Fence ? |  | Field survey - Vehicle
[17 empty] | Monitoring Structure ? |  | Field survey - Boat
Field (attribute) | Title | Purpose | Treatment) method | Management Aim | Species | Species common name | Target species arrangement | Target species coverage % | Number of weed species identified | Number of weed species treated | On ground works agent (Agent doing the work/delivery) | On ground works agent name | Total volunteer number | Total volunteer hours |  |  |  |  | Field Survey - Aerial - Drone | LOOKUPS FOR BUDGET
shapefile field name abbr | Title | Purpose | TreatmMeth | MgtAim | Species_1 | Sp1ComName | SpArrangmt | SpCoverag | NumSppId | NumSpTreat | OnGrndAg | OnGrdAgNam | VoluntNum | VoluntHour |  |  |  | Assessment purpose | Field Survey - Aerial - Fixed wing | Project management | lead agency
Valid value | Weed Control | Access/amenity | Biological | Asset based protection | Select taxon ID from Victorian Biodiversity Atlas (VBA) |  | Scattered individuals | Number | Number | Number | Contractor | Organisation name | Number | Number | Initial weed control | Weed Control | Weed control purpose | Search and detect | Field Survey - Aerial - Helicopter | On-ground delivery - specify in next column (e.g. pig control, cultural heritage assessment) | contractor
|  | Fire protection | Chemical | Containment |  |  | Small patches |  |  |  | Landowner | Not recorded (select for contractor & Landowner) |  |  | Follow-up weed control | Weed Assessment | Prevention | Specimen collection and/or ID | Other indirect survey (e.g. track or scat analysis) | Traditional Owner decision making and participation costs* | traditional owner
|  | Protect Aboriginal/Traditional Owner cultural heritage | Manual | Eradication |  |  | Large patches |  |  |  | Traditional Owner |  |  |  | Both primary and follow-up |  | Eradication | Delimiting survey | Vegetation impact survey | Comms and stakeholder engagement | volunteers
|  | Protect agriculture | Mechanical | Prevention |  |  | Majority coverage |  |  |  | Managing organisation staff | [5 empty] | Containment | Post-treatment monitoring | Field Survey - Camera traps | Research, monitoring and evaluation | other agency
|  | Protect biodiversity | Fire |  |  |  | Complete coverage |  |  |  | Volunteers/community group | [5 empty] | Asset-based protection |  | Field Survey - Transects - Sign or impacts | Other - contingency funding
|  | Protect water | Heat | [15 empty] | Field Survey - Biological sampling | Other - baits
Spatial feature | Polygon (projection must be GDA94) | [17 empty] | Field Survey - Genetic sampling | Other - vehicle and incidentals
[19 empty] | Model | Other - training
Species: Select taxon ID from Victorian Biodiversity Atlas (VBA) | [18 empty] | Capture (cage, box, net etc) | Other - capital item
Animal control: pest or exotic animals, overabundant or out of range native wildlife. | [18 empty] | Desktop / Literature review | Other - specify in next column
Pest animal or overabundant exotic or native wildlife management. | [18 empty] | Other
Level of delivery - baiting
Field (attribute) | Title | Type | Purpose | Management aim | Treatment method | Species | Species common name | Number of animals treated | On ground works agent (Agent doing the work/delivery) | On ground works agent name | Total volunteer number | Total volunteer hours | No. of bait stations within the spatial feature | Frequency of check & replace | Baiting period | Duration of trapping/weeks
shapefile field name abbr | Title | Type | Purpose | MgtAim | TreatMeth | Species | SpCommName | NumAnTreat | OnGrndAg | OnGrdAgNam | VoluntNum | VoluntHour | NumBaitSta | Frequency | BaitPeriod | DuratTrap |  | Pest Animal Assessment
Valid value | Pest animals | Herbivore | Protect Aboriginal/ Traditional Owner cultural heritage | Asset based protection | Bait | Select taxon id from Victorian Biodiversity Atlas (VBA) |  | Number | Contractor | Organisation name | Number | Number | · Number | Weekly | Number | Number |  | Fox Control
| Over abundant wildlife (includes exotic wildlife (deer)) | Predator | Protect agriculture | Containment | Biological |  |  | For bait station baiting this can be bait take. | Landowner |  |  |  |  | Fortnightly |  |  |  | Deer Control
|  | Nuisance | Protect biodiversity | Eradication | Destroy in situ |  |  | Trapping, this will be the number of animals trapped | Traditional Owner |  |  |  |  | Monthly |  |  |  | Rabbit Control
|  |  | Protect water | Prevention | Disturb |  |  |  | Managing organisation staff |  |  |  |  | Other |  |  |  | Pig Control
[5 empty] | Fertility control |  |  |  | Volunteers/ community group | [8 empty] | Goat Control
[5 empty] | Fence | [12 empty] | Cat Control
[5 empty] | Fumigate | [12 empty] | Horse Control
Ground shoot
Harbour destruction
Aerial shoot
Manual removal
Muster
Translocate
Trap
Spatial feature | Polygon (projection must be GDA94)
Bait/Trap: Additional information is required. See Level of delivery – baiting, and Level of delivery – trapping
Species: Select taxon ID from Victorian Biodiversity Atlas (VBA)
On ground works agent name. Optional, this may be published. Do not record Contractor or Land Owner
Fence
Construction and maintenance of fences.
Field (attribute) | Title | Type | Stage of delivery | Purpose | Change in access | Specific type | Species access change | Area fenced (Ha) | On ground works agent (Agent doing the work/delivery) | On ground works agent name | Total volunteer number | Total volunteer hours
Valid value | Fence | Internal | Install (new) | Agricultural | Contain | Bollard | Deer |  | Contractor | Organisation name | Number | Number
|  | External | Maintain (repair) | Protect Aboriginal/ Traditional Owner cultural heritage | Exclude | conventional fence | Domestic stock |  | Landowner
|  | Temporary internal | Modify | Protect biodiversity |  | Predator proof fence | Human and related activities |  | Traditional Owner
|  | Temporary external | Remove | Protect water |  | Electric fence | Native species |  | Managing organisation staff
|  |  | Replace |  |  | Mesh fence | Pest herbivore |  | Volunteers/ community group
[6 empty] | Waterway | Pest predator
[6 empty] | Combination | Native species
Revegetation/Restoration
Revegetating or restoring (often cleared) land, and marine and coastal environments.
Field (attribute) | Title | Type | Provenance | Stage of delivery | Method | Target EVC / Biotope code | On ground works agent (Agent doing the work/delivery) | On ground works agent name | Total Volunteer number | Total volunteer hours | Revegetation
shapefile field name abbr | Title | Type | Provenance | StgDelivr | Method | EVC_Biotop | OnGrndAg | OnGrdAgNam | VoluntNum | VoluntHour
Valid value | Revegetation / restoration | EVC structure and diversity | Climate change adjusted | Establish | Aerial sowing | NA for mixed species | Contractor | Organisation name | Number | Number
|  | EVC multi strata | Combination climate change adjusted and local. | Maintain | Brush mulching |  | Landowner | Not recorded
|  | EVC overstory | Local | Modify | Direct sowing |  | Traditional Owner
|  | Mixed species |  |  | Hydro mulching |  | Managing organisation staff
|  | Biotope structure and diversity |  |  | Long-stem planting |  | Volunteers/ community group
|  | Biotope overstory |  |  | Seedbank introduction
Seedling planting
Maintenance
Soil preparation
Artificial kelp
Spatial feature | Polygon (projection must be GDA94)
Assessment
Assessments for information gathering that may or may not lead to management actions.
Field (attribute) | Title | Type | Data Storage | Database Id | Assessment method | Related Activity | Related Activity Stage | On ground works agent (Agent doing the work/delivery) | On ground works agent name | Total Volunteer number | Total volunteer hours
shapefile field name abbr | Title | Type | DataStorag | DataBaseID | AssessMeth | RelatActiv | RelActvStg | OnGrndAg | OnGrdAgNam | VoluntNum | VoluntHour
Valid value | Assessment | Agronomic | Agency database | Identifier for the record in the database e.g. VBA or Birdata survey id | Inspection | Animal control | Pre treatment | Contractor | Organisation name | Number | Number
|  | Cultural | Atlas of living Australia |  | Model | Habitat condition | Post treatment | Landowner | Not recorded (select for contractor & Landowner)
|  | Ecological | Birdlife Australia Birdata |  | Survey | Management agreement | Na | Traditional Owner
|  | Fauna | Coastkit |  | Remote | Research and monitoring |  | Managing organisation staff
|  | Flora | iNaturalist |  | Visual | Revegetation and restoration |  | Volunteers/ community group
|  | Geological | Litterwatch |  | Other | Threatened species response.
|  | Geospatial | Monitoring sites database |  |  | Weed control
|  | Habitat hectare | Mdba |  |  | Water
|  | Heritage | Salinity register |  |  | N/a
|  | Invasive species | Star
|  | Litter audit | Victorian Biodiversity Atlas
|  | Property | Victoria Water Data Warehouse
|  | Social | VMCP
|  | Soil | Waterwatch/ estuary watch data warehouse
|  | Groundwater | NA
|  | Surface water | Other
Weather
Threatened species
Other
Monitoring structure
Structures and locations for monitoring and surveillance.
Field (attribute) | Title | Type | Stage of delivery | Purpose | Related Activity | On ground works agent (Agent doing the work/delivery) | On ground works agent name | Total Volunteer number | Total volunteer hours
Valid value | Monitoring structure | Artificial substrate | Install | Fauna | Animal control | Contractor | Organisation name | Number | Number
|  | Bore | Maintain | Flora | Habitat condition | Landowner | Not recorded (select for contractor & Landowner)
|  | Buoy/mooring | Modify | Groundwater | Management agreement | Traditional Owner
|  | Camera trap | Remove | Soil | Research and monitoring | Managing organisation staff
|  | Hide | Replace | Surface water | Revegetation and restoration | Volunteers/ community group
|  | Measuring station |  | Weather | Threatened species response.
|  | Photo point |  | Water quality | Weed control
|  | Trap |  | Wave | Water
|  | Quadrats |  |  | N/a
Recruitment plates
Song meter
Depth gauge
Flow meter
Other
Research and monitoring
Research and monitoring to fill knowledge gaps.
Field (attribute) | Title | Type | Species | Species common name | Specific activity | Permit No | On ground works agent (Agent doing the work/delivery) | On ground works agent name | Total Volunteer number | Total volunteer hours
Valid value | Research and monitoring | Ecological |  |  | Behaviour |  | Contractor | Organisation name | Number | Number
|  | Geophysical |  |  | Life history/physiology |  | Landowner | Not recorded (select for contractor & Landowner)
|  | Social |  |  | Threats |  | Traditional Owner
[5 empty] | Population and distribution |  | Managing organisation staff
Volunteers/ community group
Threatened species response
Actions taken to manage threatened species.
Field (attribute) | Title | Purpose | Type | Treatment area | Species | No. of individuals | On ground works agent (Agent doing the work/delivery) | On ground works agent name | Total Volunteer number | Total volunteer hours
Valid value | Threatened species response | Restore biological community | Caging |  |  | Number | Contractor | Organisation name | Number | Number
|  | Restore individual species | Captive breeding |  |  |  | Landowner | Not recorded (select for contractor & Landowner)
|  |  | Collect/ store seed or vegetative material |  |  |  | Traditional Owner
|  |  | Connectivity interventions |  |  |  | Managing organisation staff
|  |  | Cryobanking |  |  |  | Volunteers/ community group
Establish new population
Fenced-wild captive breeding
Genetic interventions
Genetic testing
Germplasm
Inoculate soil
Pollination
Propagation
Species introduction/ reintroduction
Supplementary watering/feeding
Wild to wild translocation.
Other
Engagement Event
Events for engaging communities.
Field (attribute) | Title | Purpose | Type of engagement event | Role | Event Name | Number of Participants | Event Length | Number of Events | Target Audience | Focus | Campaign Name | On ground works agent (Agent doing the work/delivery) | On ground works agent name | Total Volunteer number | Total volunteer hours
shapefile field name abbr | Title | Purpose | TypeEngEvn | Role | EventName | ParticNum | EventLengt | NumEvents | TargAud | Focus | CampgName | OnGrndAg | OnGrdAgNam | VoluntNum | VoluntHour
Valid value | Engagement event | Inform | Citizen advisory committee | Coordinate |  | Number | Hours | Number | Agency staff | Agricultural | Name | Contractor | Organisation name | Number | Number
|  | Consult | Citizen juries | Sponsor |  |  |  |  | CBNRM group | Conservation management techniques | NA | Landowner | Not recorded (select for contractor & Landowner)
|  | Involve | Citizen science | Support |  |  |  |  | General community | Data management and reporting |  | Traditional owner
|  | Collaborate | Conference | [5 empty] | Aboriginal community | General occupational health and safety |  | Managing organisation staff
|  | Empower | Field day | [5 empty] | Land managers | Environmental threats |  | Volunteers/ community group
|  | Diverge | Meeting | [5 empty] | Schools | Species population and distribution
|  | Converge | Open house | [5 empty] | Youth | Survey and monitoring
|  | Educate | Presentation | [5 empty] | Other | Recruitment
|  |  | Survey | [6 empty] | Planning
|  |  | Training | [6 empty] | Nature and cultural awareness
|  |  | Volunteering event | [6 empty] | Act for nature
|  |  | Web feedback | [6 empty] | Connect with nature
|  |  | Workshop | [6 empty] | Behaviour change
Other
DEECA Regions | PV Regions | LGA's | CMA's | Type of co-investment (cash or in-kind)
Hume | Eastern | Alpine Shire | Corangamite | Cash
Gippsland | Melbourne | Ararat Rural City | East Gippsland | In-kind
Barwon SW | Northern | Ballarat City | Glenelg Hopkins
Loddon Mallee | Statewide | Banyule City | Goulburn Broken
Grampians | Western | Bass Coast Shire | Mallee
Port Phillip |  | Baw Baw Shire | North Central
Statewide |  | Bayside City | North East
|  | Benalla Rural City | Melbourne Water
|  | Boroondara City | West Gippsland
|  | Borough of Queenscliffe | Wimmera
Brimbank City
Buloke Shire
Greater Bendigo City
Campaspe Shire
Cardinia Shire
Casey City
Central Goldfields Shire
Colac Otway Shire
Corangamite Shire
Darebin City
Greater Dandenong City
East Gippsland Shire
Frankston City
Gannawarra Shire
Glen Eira City
Glenelg Shire
Golden Plains Shire
Greater Bendigo City
Greater Dandenong City
Greater Geelong City
Greater Shepparton City
Hepburn Shire
Hindmarsh Shire
Hobsons Bay City
Horsham Rural City
Hume City
Indigo Shire
Kingston City
Knox City
Latrobe City
Loddon Shire
Macedon Ranges Shire
Manningham City
Mansfield Shire
Maribyrnong City
Maroondah City
Melbourne City
Melton City
Merri-bek City
Mildura Rural City
Mitchell Shire
Moira Shire
Monash City
Moonee Valley City
Moorabool Shire
Mornington Peninsula Shire
Mount Alexander Shire
Moyne Shire
Murrindindi Shire
Nillumbik Shire
Northern Grampians Shire
Port Phillip City
Pyrenees Shire
Borough of Queenscliffe
Greater Shepparton City
South Gippsland Shire
Southern Grampians Shire
Stonnington City
Strathbogie Shire
Surf Coast Shire
Swan Hill Rural City
Towong Shire
Wangaratta Rural City
Warrnambool City
Wellington Shire
West Wimmera Shire
Whitehorse City
Whittlesea City
Wodonga City
Wyndham City
Yarra City
Yarra Ranges Shire
Yarriambiack Shire